## Summary
Tarnovell Bioscience Group ¦ SharePoint migration tracker - September 2026
Snapshot date | 25/09/2026
Owner | Sofia Lindervik, Integration Director
Scope | Local shares for firms A-F preserved as archive roots; firm G (Osterquill) listed for pre-completion planning only
Procedure | Archive Migration Ownership Procedure v2 (June 2025)
Note | Close a migration task only when inventory, permission mapping, ownership checks and any exception sign-off are recorded under Procedure v2. A completed copy is insufficient.

## Share
Firm | Share scope | Archive-root plan | Retention decision | Ownership check | Leaver folders | Status | Notes
A | Historical chemistry records; inventory reference pending | Preserve separate local archive root; mapping pending | Retain originals | Confirmation required | Ownership check required | Open | Acceptance evidence pending: inventory, permissions and ownership; preserve original scientific records
A | Chemistry shared records; inventory reference pending | Preserve separate local archive root; mapping pending | Retain originals | Confirmation required | Ownership check required | Open | Acceptance evidence pending: inventory, permissions and ownership; preserve original scientific records
B | Screening records; inventory reference pending | Preserve separate local archive root; mapping pending | Retain originals | Confirmation required | Ownership check required | Open | Acceptance evidence pending: inventory, permissions and ownership; preserve original scientific records
B | Assay protocols; inventory reference pending | Preserve separate local archive root; mapping pending | Retain originals | Confirmation required | Ownership check required | Open | Acceptance evidence pending: inventory, permissions and ownership; preserve original scientific records
C | Bioanalysis raw records; inventory reference pending | Preserve separate local archive root; mapping pending | Retain originals | Confirmation required | Ownership check required | Open | Acceptance evidence pending: inventory, permissions and ownership; preserve original scientific records
C | Draft and superseded reports; inventory reference pending | Preserve separate local archive root; mapping pending | Review before move | Confirmation required | Ownership check required | Open | Acceptance evidence pending: inventory, permissions and ownership; preserve original scientific records
D | Computational project records; inventory reference pending | Preserve separate local archive root; mapping pending | Retain originals | Confirmation required | Ownership check required | Open | Acceptance evidence pending: inventory, permissions and ownership; preserve original scientific records
E | Stability records; inventory reference pending | Preserve separate local archive root; mapping pending | Retain originals | Confirmation required | Ownership check required | Open | Acceptance evidence pending: inventory, permissions and ownership; preserve original scientific records
F | Formulation records; inventory reference pending | Preserve separate local archive root; mapping pending | Retain originals | Confirmation required | Ownership check required | Open | Acceptance evidence pending: inventory, permissions and ownership; preserve original scientific records
G | Osterquill local archive (planning only) | No migration before completion | Hold apart after completion pending access and QA mapping | Pending post-completion review | Pending post-completion review | Planning | Planned completion 1 October 2026; not yet a group firm at this snapshot

## Open items
# | Item | Owner | Due | Blocking | Status
1 | Confirm ownership of B assay protocol records | Biology lead, B | To be agreed | Move of B protocol records | Open
2 | Confirm ownership of A chemistry leaver folders | Sofia Lindervik with Praneel Pal | To be agreed | Move of A chemistry records | Open
3 | Review C draft reports against superseded versions | C QA lead | To be agreed | Retention decision for C drafts | Open
4 | Complete F permission mapping and acceptance checks | F IT lead | To be agreed | F sign-off | Open
5 | Confirm E stability record retention and ownership | E study manager | To be agreed | E retention sign-off | Open
6 | Confirm D computational share permissions | D site leadership | To be agreed | D migration acceptance | Open
7 | Osterquill access and QA mapping plan | Yasmin Farhat | Before 1 October 2026 completion | G onboarding | Planning

## Log
Date | Change | By
25/09/2026 | September snapshot: A-F acceptance checks remain open; Osterquill listed for pre-completion planning only | Sofia Lindervik