## Amendments
DRAFT: OT-25-S0229 protocol amendment tracker
Study | OT-25-S0229 |  | Status | On hold
LIMS | OQ/2025/003671 |  | Client | Valquessia Pharmaceuticals SpA
No. | Amendment | Raised by | Date raised | Status | Open question
1 | Pre-dosing formulation hold: new formulation to be qualified before dosing starts | Kathryn Holmes | 10/06/2025 | Open | Qualification report date
2 | Upper dose level in the range-finding design | Lucia Moretti | 10/06/2025 | Draft | Sponsor confirmation of the top dose
3 | Dosing schedule for the recovery arm | Naomi Takamori |  | Not started
4 | Clinical observation scoring sheet
5 | Necropsy and pathology sampling list | Nathan Wade
Draft. Sections 3 to 5 of the protocol remain under review.
Note on E6: Upper dose cell is still open. Nothing goes to Valquessia until Naomi has seen the revised rationale.
Note on B7: Dosing schedule for the recovery arm not drafted. Rachel to take it on once the vehicle is signed off.

## Dose levels
Group | Dose (mg/kg/day) | Notes
Control | Vehicle | Control vehicle to be aligned with the qualified formulation; amendment approval pending
Low |  | To be set from the range-finding design
Mid
High |  | Upper level pending sponsor confirmation
Animal numbers and sex split: to be confirmed at the study start meeting.
Pre-dosing hold: no animal dosing results or tolerated-dose conclusion recorded.
Note on B4: Leave blank until the amendment is approved. I'd rather see gaps than a number nobody has agreed.