## Status
Brand migration status - September 2026
Owner | Sofia Lindervik, Integration Director
Brand rules | Tarnovell Brand Guidelines v1 (February 2020), as updated for the common master
Brand line | Tarnovell Bioscience Group
Footer | Tarnovell Bioscience Group ¦ Confidential
Firm | Brand adoption | Materials on common master | Open items | Last reviewed | Owner
A Vellacombe Discovery | Complete | Yes | None | 18/09/2026 | Nils Bergstrom
B Brindlewythe Biosciences | Complete | Yes | Client report templates | 18/09/2026 | Judith Wilson
C Merrivoss Bioanalysis | Complete | Yes | Email signatures in the US office | 21/09/2026 | Judith Wilson
D Quenverell Computational | Complete | Yes | Software documentation headers | 22/09/2026 | Praneel Pal
E Westravelle Analytical | Complete | Yes | Stability report cover pages | 23/09/2026 | Ruggero Tonisto
F Durnesswick Laboratories | In progress | Partly | Formulation SOP headers, two sets of slide decks, website footer | 25/09/2026 | Lawrence Hutchinson
G Osterquill Toxicology | Legacy | No | Held apart. No changes until the archive is mapped and access is agreed | 25/09/2026 | Yasmin Farhat
Note on D14: Legacy Osterquill client and study documents are not to be restyled. Only the group-facing materials are in scope for G after completion.

## Actions
# | Action | Owner | Due | Status | Note
1 | Replace legacy header on Durnesswick formulation SOPs | Lawrence Hutchinson | 16/10/2026 | Open | Controlled copies only; superseded copies stay as issued
2 | Update slide masters for the two Durnesswick decks | Lawrence Hutchinson | 30/10/2026 | Open | Confirm with the Durnesswick business development lead first
3 | Replace Durnesswick website footer | Ruggero Tonisto | 30/10/2026 | Open | Subject to web team release window
4 | Confirm G brand position for post-completion correspondence | Daniel Grellacott | Before 1 October 2026 completion | Open | Decision needed before any G material is issued under the group brand
5 | Close email signature exceptions in the US office | Judith Wilson | 09/10/2026 | Open | Two signatures still carry the earlier firm line
6 | Confirm A-E master library is locked | Nils Bergstrom | 15/10/2026 | Open | Read-only access for local editors to be checked