Quenverell Computational Ltd, a Tarnovell company

# Immune-cell RNA-seq reanalysis and target ranking

Proposal for Corvenlith Therapeutics

Engagement: QV.23.100

Date: 11/09/2023

Prepared by: Dr T. Zawiernicki, Head of Bioinformatics

# 1 The biological question

Corvenlith Therapeutics has RNA-seq from immune cells stimulated in vitro, from healthy and patient donors, with unstimulated and stimulated samples from each donor, and a candidate list of inflammatory targets. The question is which candidates respond to stimulation consistently across donors, and which differ between patient and healthy donors.

# 2 Data and provenance

Client-supplied FASTQ files and sample manifest

Donor, batch and stimulation metadata reconciled against the manifest before any analysis

Public reference expression data for tissue context

# 3 Approach

Data acceptance: read QC, sample identity checks, outlier review

Within-donor stimulation contrasts with donor as a blocking factor (paired design)

Patient versus healthy comparison with an estimable group model (donor as a random effect, with age and sex as covariates); confirmed after manifest review

Sensitivity analysis: results with and without the two flagged donors

Omics target prioritisation: evidence score per candidate combining expression, pathway context and tissue specificity

Model uncertainty will be reported plainly; candidates whose ranking depends on a single donor will be flagged rather than dropped.

# 4 Deliverables and timing

Data acceptance note and interim readout (about 3 weeks after data receipt)

Final readout deck and ranked target cards

Analysis notebook and versioned pipeline record

# 5 Price

| Work package | Price (GBP) |
| --- | --- |
| Data acceptance and QC | £8,200 |
| Differential expression and sensitivity analysis | £24,600 |
| Target prioritisation and target cards | £16,800 |
| Readouts | £4,800 |
| Total | £54,400 |

Fixed price, excluding VAT. Additional datasets quoted separately.

# 6 Notes

Corvenlith Therapeutics is an existing Quenverell client and is a separate company from the similarly named group account; please quote the Corvenlith name exactly on the purchase order.

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
| Tomasz Zawiernicki | Head of Bioinformatics |  | 11/09/2023 |