## Slide 1: Rennelwick receptor programme: co-crystal-guided analogues
VD-18-131 readout | Vellacombe Discovery Ltd | 24 January 2019

## Slide 2: Where we are
Programme started 05/11/2018 with the Rennelwick Institute Drug Discovery Unit
Institute's structural biology collaborators supplied two X-ray co-crystal structures in December
Chemistry plan revised against the structures
Delivery lot for binding studies completed this week
Vellacombe Discovery Ltd | Confidential 2

## Slide 3: What the co-crystal structures showed
Ligand sits deeper in the pocket than the docking model assumed (observed in the co-crystal structures)
Overlaying the bulky ortho analogue on the observed pose predicts a clash with a backbone carbonyl
  Hypothesis for the flat SAR in the first analogue set
Room for a smaller group pointing to solvent
Vellacombe Discovery Ltd | Confidential 3
Notes: Structures belong to the Institute; images not reproduced here. Ask Rennelwick before showing externally.

## Slide 4: Hypothesis
Replace the ortho substituent with a less hindered group
Keep the hinge-facing amide unchanged
Use the solvent vector for solubility
Vellacombe Discovery Ltd | Confidential 4

## Slide 5: Route
Common intermediate RI13-INT-07 from route scout 1
Two-step coupling then amide formation
Route risk: regioisomer in step 1
Isolated material by crystallisation
Purity release by LCMS area percent
Compound cards with every lot
Vellacombe Discovery Ltd | Confidential 5

## Slide 6: Route gate (17/12/2018)
Regioisomer reduced by running step 1 at lower temperature (see route scout note RI13-RS-02)
Gate passed; analogue preparation started
Vellacombe Discovery Ltd | Confidential 6

## Slide 7: Delivered
Delivery lot RI13-L01 for binding studies: analogues RI13-001 to RI13-008
Identity confirmed by 1H NMR and LC-MS
Release records with the compound cards for lot RI13-L01
Vellacombe Discovery Ltd | Confidential 7

## Slide 8: Proposed versus isolated
All proposed analogues of the first design round isolated (RI13-001 to RI13-008)
Two solvent-vector analogues (RI13-009, RI13-010) proposed but not yet made
Isolated material only is reported as delivered
Vellacombe Discovery Ltd | Confidential 8

## Slide 9: Open questions for Rennelwick
Binding data on lot 1 before the next design round
A third co-crystal structure with the smaller substituent would confirm the pose
Solubility of the solvent-vector analogues
Vellacombe Discovery Ltd | Confidential 9

## Slide 10: Next analogue
Pending binding data: extend the solvent vector with polar groups
Hold the hinge amide
Next readout planned for March
Vellacombe Discovery Ltd | Confidential 10

## Slide 11: Team
Dr R. Calderwood (programme lead)
Dr H. Darwish (synthesis)
C. Fenwick (analytical release)
Vellacombe Discovery Ltd | Confidential 11