## Gate tracker
FM20 hERG screen: screen gate tracker
Project | BW25_0486
LIMS accession | B-ACC-2025-08282
Client | Farnovessa Medicines
Series | FM20 imidazolidinone series 20
Compounds | 32
Status | On hold since 15/12/2025. Paused while the nomination committee reviews a new efficacy concern. Not related to the assay.
Screen gate | Planned | Actual | Owner | Status
Quote |  | 13/10/2025 | John Mckinney | Done
Screen start |  | 24/11/2025 | Leila Benmezroun | Done
Interim readout |  | 15/12/2025 | Bethany Rowcroft | Done
Nomination support decision |  |  | Bethany Rowcroft | Open
Plate allocation check |  |  | Ines Alvarado | TODO
Completion |  |  | Bethany Rowcroft
Note on A7: Do not send anything to Farnovessa until the nomination committee has replied.
Note on E14: TODO: plate 4 allocation is still missing. Stéphane to confirm before anyone signs the readout.

## Shipment receipt
Shipment receipt
Shipment | Received | Compounds | Condition | Checked by
Shipment 1 | 19/11/2025 |  | Intact | Henning Flantz
Shipment 2
Shipment 3
Count each shipment against the sample card list before release to plates.

## Plate allocation
Plate allocation
Plate | Compound block | Operator | Run date | Status
1 | FM20-02000 to FM20-02010 | Jason Scanlon | 25/11/2025 | Done
2 | FM20-02012 to FM20-02018 | Jason Scanlon |  | Done
3 |  |  |  | Not started
4

## hERG IC50
hERG IC50, automated patch clamp, rows read before the pause
The remaining compounds were not read before the pause. TODO: reconcile this sheet with the benchmark before anyone quotes a figure.
Compound | IC50 cell 1 (µM) | IC50 cell 2 (µM) | IC50 cell 3 (µM) | IC50 geomean (µM) | % inhibition @10 µM | n cells (finite) | QC note
FM20-02000 | 5.4 | 5.3 | 4.8 | 5.2 | 67 | 3 (3)
FM20-02010 | 0.6 | 1.2 |  | 0.83 | 94 | 2 (2)
FM20-02016 | 12 | 21 |  | 16 | 42 | 2 (2)
FM20-02018 | 2.4 | 1.5 |  | 1.9 | 84 | 2 (2)
FM20-02022 | 18 | 12 | 14 | 15 | 45 | 3 (3)
FM20-02028 | 18 | 12 | 26 | 18 | 34 | 3 (3)
FM20-02034 | 0.36 | 0.43 |  | 0.39 | 88 | 2 (2)
FM20-02040 | 3.6 | 2.9 |  | 3.2 | 75 | 2 (2)
FM20-02048 | 6 | 8.6 |  | 7.2 | 59 | 2 (2)
FM20-02052 | 0.83 | 1.1 |  | 0.97 | 91 | 2 (2)
FM20-02054 | 2.2 | 1.1 |  | 1.5 | 92 | 2 (2)
FM20-02060 | 3.9 | 5.6 |  | 4.7 | 65 | 2 (2)
FM20-02064 | 5.2 | 7.1 |  | 6.1 | 66 | 2 (2)
FM20-02066 | 2.7 | 3.6 |  | 3.1 | 76 | 2 (2)
FM20-02078 | 1.4 | 1.3 |  | 1.4 | 88 | 2 (2)
FM20-02082 | 2.1 | 2.4 |  | 2.3 | 77 | 2 (2)
FM20-02084 | 11 | 5 | 17 | 9.9 | 55 | 3 (3)
FM20-02096 | 1.2 | 1.7 |  | 1.4 | 82 | 2 (2)
FM20-02108 | 1.7 | 4 |  | 2.6 | 75 | 2 (2) | Seal resistance <500 MΩ in one cell; cell excluded
FM20-02114 | >30 | >30 |  | >30 | 26 | 2 (0)
FM20-02120 | 1 | 0.97 |  | 1 | 95 | 2 (2)
Top concentration 30 µM; 6-point, 3-fold dilution; positive control E-4031 IC50 15 nM (acceptance 5-50 nM)
Compound IC50 = geometric mean of finite cell IC50s when they are the majority of accepted cells; otherwise reported as >30 µM (or >10 µM where solubility-limited)
Work stopped; partial data only
Note on A2: Benchmark counts the full set, these rows do not. Keep both until the readout is signed off.