## Slide 1: DT-R delivery lot 2: INTERIM inventory
Doventhar Therapeutics | VD-26-113 | 16 Sep 2026 Dr H. Darwish | Replacement-core gate open

## Slide 2: Position today: side chains isolated, coupling held
The first basic side-chain intermediates have been isolated.
Final coupling awaits release of Doventhar Therapeutics’ replacement core.
An isolated side-chain intermediate is not a completed DT-R analogue.
Final delivery-lot composition: [TBC].
Vellacombe Discovery Ltd, a Tarnovell company | Confidential 2

## Slide 3: Intermediate inventory — status only
Material class | Position at 16 Sep 2026 | Open inventory field
Basic side-chain intermediates | First intermediates isolated | Compound-card identifiers and mg [TBC]
Replacement core | Client release awaited | Release reference and available amount [TBC]
Final coupled material | Coupling gate pending | Final identity and isolated yield [TBC]
Delivery lot 2 | Interim planning only | Released contents [TBC]
Vellacombe Discovery Ltd, a Tarnovell company | Confidential 3

## Slide 4: What the isolated intermediates establish
The side-chain route has produced isolated material.
Keep each intermediate linked to its compound card.
Reconcile identity and amount before charging the final coupling.
The replacement core remains a separate dependency.
No final-coupling outcome can be concluded from the side-chain isolation.
Allocation to final analogues: [TBC].
Vellacombe Discovery Ltd, a Tarnovell company | Confidential 4

## Slide 5: Replacement-core release: required handover
Doventhar Therapeutics to provide the replacement-core release reference.
Confirm the released material matches the intended coupling input.
Replacement-core amount and release date: [TBC].
Keep the final coupling on hold until the release dependency is resolved.
Vellacombe Discovery Ltd, a Tarnovell company | Confidential 5

## Slide 6: Final coupling route scout
Start from the isolated basic side-chain intermediates after the core is released.
Record the charged material identities and quantities on the route scout.
Assess conversion and recovery separately.
Coupling conditions and final isolation sequence: [TBC].
Proposed final structures remain proposals until isolated.
Vellacombe Discovery Ltd, a Tarnovell company | Confidential 6

## Slide 7: Owners for the next route gate
Hassan Darwish: intermediate inventory and coupling preparation.
Clara Fenwick: analytical link for material carried forward.
Ruth Calderwood: final-coupling route gate.
Doventhar Therapeutics: replacement-core release.
Inventory reconciliation date: [TBC].
Next client update: [TBC].
Vellacombe Discovery Ltd, a Tarnovell company | Confidential 7

## Slide 8: Interim conclusion: preserve the material, wait for the core
First side-chain intermediates are isolated.
Final coupling remains dependent on replacement-core release.
Complete the compound-card inventory before committing material.
Final lot release and programme completion: [TBC].
No final analogue delivery is claimed at this interim gate.
Vellacombe Discovery Ltd, a Tarnovell company | Confidential 8