## Basis
Integration benefits baseline - December 2025
Prepared by | Andrea Beckett, Group Finance Director
Baseline date | 31/10/2025
Reporting period | Financial year 2025 to date, to 30/11/2025
Group reporting currency | GBP
Local currencies | Retained for each firm and translated at the monthly group rate. US firms (C and F) report in USD locally.
Status | Final for the December 2025 integration review
Rule | Realised savings are only those evidenced in the ledger after the cost has left the firm. Opportunities stay in the second sheet until the Integration Steering Group approves them.
Rule | Local scientific operations are not reduced by this case. Savings come from shared administration only.
Note on B6: The historical discounts for the firms that have not moved to the common price list are still applied in the ledger. They are not part of this baseline.

## Realised
Firm | Category | Basis | Period | Status | Assumption
A Vellacombe Discovery | Shared finance processing | Ledger posting | Jan-Nov 2025 | Realised | Headcount in the old finance team not backfilled
B Brindlewythe Biosciences | Insurance renewal | Signed renewal | Jan-Nov 2025 | Realised | Single group policy from the 2025 renewal date
C Merrivoss Bioanalysis | Software licences | Licence register | Jan-Nov 2025 | Realised | Duplicate licences cancelled; no change to user count
D Quenverell Computational | Office consolidation | Lease notice | Jan-Nov 2025 | Realised | Notice period ends in the 2026 financial year
E Westravelle Analytical | Shared finance processing | Ledger posting | Jan-Nov 2025 | Realised | Month-end close now run from the group ledger
F Durnesswick Laboratories | Travel booking | Booking platform report | Aug-Nov 2025 | Realised | Only from the date the group booking account went live
Note on E7: Realised here means posted and evidenced. Anything not yet in the ledger goes on the Opportunities sheet.

## Opportunities
Firm | Opportunity | Owner | Approval | Counted in case | Note
A Vellacombe Discovery | Consolidate payroll runs | Nils Bergstrom | Not approved | No | Depends on the HR and payroll consolidation
B Brindlewythe Biosciences | Shared reagent purchasing | Ruggero Tonisto | Under review | No | Commercial terms with suppliers still being negotiated
C Merrivoss Bioanalysis | Shared utilities contract | Andrea Beckett | Not approved | No | Site contract runs to 2027
D Quenverell Computational | Cloud hosting consolidation | Sofia Lindervik | Not approved | No | Requires security review first
E Westravelle Analytical | Shared calibration service | Ruggero Tonisto | Under review | No | Quality sign-off outstanding
F Durnesswick Laboratories | Group insurance review | Andrea Beckett | Not approved | No | Awaiting broker comparison
Group | Finance shared services fees | Andrea Beckett | Approved | No | Recorded as a cost of the integration, not a saving

## Notes
Assumption | Basis for the figure | Reviewed by
Currency | Local currency converted at the group rate for the period; no rate is fixed in this baseline | Andrea Beckett
Period | Figures are cut off at 30/11/2025. December postings are picked up in the next baseline | Andrea Beckett
Exclusions | Local scientific headcount, client pricing and historical discounts | Andrea Beckett
Double counting | Items already in the price harmonisation workstream are not counted here | Sofia Lindervik