## Summary
VD-26-091 NLM-A fluorinated building blocks: scout tracker
Vellacombe Discovery Ltd, a Tarnovell company
Client | Nelmudara Biosciences
Programme | VD-26-091
LIMS | VA20260826
Status | Interim, 21 Aug 2026. Route scout delayed.
Price | GBP 45,400
Lead | Dr R. Calderwood
Current position | The unstable boronate has delayed the route scout, which started on 20 Jul 2026. The team is evaluating a protected alternative with the client. Timing and scope of further work remain [TBC].
Route gate | Not passed
Note on B11: Client decision on the protected alternative still pending. Do not quote a date until they reply.

## Attempt log
Record | Route issue | Conditions | Scale (mg) | Outcome | Next step
Boronate route scout | Unstable boronate | See route scout records |  | Route scout delayed | Evaluate protected alternative with client
Protected alternative | Under evaluation | [TBC] |  |  | Client decision pending
Note on C2: Refer to the route scout records for attempt details; analytical interpretation is not transcribed here.

## Client decisions
Decision | Options | Owner | Needed by | Status
Protecting group for the boronate | Protected alternative [TBC] | Nelmudara Biosciences | [TBC] | Open
Agree route implications of protected alternative | [TBC] | Nelmudara Biosciences | [TBC] | Open
Revised batch size for the scout | [TBC] | Nelmudara Biosciences |  | Open
Confirm further scout scope | [TBC] | Ruth Calderwood |  | Open
Note on D2: Decision timing still to be confirmed with the client.