## Slide 1: Integration board update
One Group, Many Practices Q2 2024 board meeting Sofia Lindervik, Integration Director

## Slide 2: Purpose of this update
Report progress on the integration programme since the board approved its scope in April
Confirm the workstream owners and their current status
Bring forward the Durnesswick integration decisions for approval
Set out the decisions on price and archive that we still need from the board
Tarnovell Bioscience Group | Confidential 2

## Slide 3: Programme principle
One Group, Many Practices: local scientific operations are retained while shared processes converge
Shared functions move to group ownership first: HR, finance, IT and commercial reporting
Local client relationships, study direction and accession numbering are not changed without a specific decision
Each firm's legacy records are kept as they are unless a retention or access decision says otherwise
Tarnovell Bioscience Group | Confidential 3

## Slide 4: Workstreams and owners
Workstream | Owner | Status at June 2024
Price harmonisation | Andrea Beckett | Started; local currencies and discounts under review
Brand migration | Daniel Grellacott | A-E use the common master; Durnesswick migration in progress
LIMS consolidation | Yasmin Farhat | Scoping; export fields drafted
Cross-sell | Ruggero Tonisto | Client identity bridge being scoped
HR and payroll | Nils Bergstrom | Directory consolidation under way for early firms
IT and SharePoint migration | Praneel Pal | Local shares to be preserved as archive roots
Tarnovell Bioscience Group | Confidential 4

## Slide 5: Durnesswick Laboratories: integration status
Durnesswick joined the group on 1 February 2024; the acquisition prompted the formal integration programme
Formulation and early CMC work continues with its own scientific leadership and client contracts
Brand migration to the common master remains in progress; confirm outstanding adoption steps with Durnesswick leadership
Durnesswick's LIMS cutover is not yet scheduled and will follow the export dictionary decision
Tarnovell Bioscience Group | Confidential 5

## Slide 6: Brand migration
Common master template and brand guide agreed with the group communications lead
Firms A to E already use the common master introduced in 2020; Durnesswick is the remaining brand migration workstream
Legacy records will not be restyled; only documents issued from migration onwards use the master
Durnesswick will migrate its templates first, followed by its signature blocks and report headers
Tarnovell Bioscience Group | Confidential 6

## Slide 7: LIMS consolidation
Draft export dictionary covers the fields that group reporting needs from each firm
Local accession numbers will be kept for all firms, which the board is asked to confirm
Cutover dates are not set; the draft plan will come back to the board after firm-level reviews
Quality review of the export fields is under way with each site head
Tarnovell Bioscience Group | Confidential 7

## Slide 8: Price harmonisation: current position
Price lists and service names are being gathered firm by firm, starting with the older acquisitions
Historical currencies and discounts are recorded as they stand and not netted off
No group price rule has been proposed yet, and no quote should be assumed to follow one
A decision on the normalisation approach is needed from the board before the mapping can be finished
Tarnovell Bioscience Group | Confidential 8

## Slide 9: Cross-sell and client identity
A client identity bridge is being built so that one customer is not treated as two by different firms
Subsidiary and lookalike name checks are required before any cross-sell approach is made
No cross-sell activity should start with a client until its identity has been checked against the bridge
Commercial leads have agreed to hold back joint approaches until the first bridge review
Tarnovell Bioscience Group | Confidential 9

## Slide 10: HR and payroll
Directory consolidation is under way and will reach firms A to F in turn
Payroll stays with each firm until its directory entries are confirmed
Staff at Durnesswick are on the group directory from the start of integration
The group will not onboard a firm's payroll until its leavers and contractors are reconciled
Tarnovell Bioscience Group | Confidential 10

## Slide 11: IT and archive migration
Local shares are being kept as archive roots rather than merged into the group estate
Leaver folders need an owner's sign-off before they move or are deleted
Retention decisions are not yet made for the older shares and are listed as open
No shared drive content will be deleted as part of the migration without written approval
Tarnovell Bioscience Group | Confidential 11
Notes: The board asked last quarter what happens to leaver folders. This is the current answer, and it will be checked again at the next update.

## Slide 12: Risks
Price mapping could lock in historical discounts that clients expect to keep, which the commercial team is watching closely
Brand migration may leave mixed templates in client hands if the legacy records are not clearly marked
LIMS cutover dates depend on firm-level reviews that have not yet been scheduled
Archive decisions could slip if ownership of leaver folders is not confirmed in time
Tarnovell Bioscience Group | Confidential 12

## Slide 13: Decisions requested from the board
Approve the Durnesswick integration plan for brand, LIMS and HR steps
Confirm that local accession numbers are retained for all firms
Agree that the price normalisation approach comes back to the board in the autumn
Note the archive hold for legacy shares until ownership checks are complete
Tarnovell Bioscience Group | Confidential 13

## Slide 14: Next steps
Workstream owners to return updated plans by the end of June 2024
Durnesswick brand migration plan to be circulated to the firm's leadership team
Client identity bridge review at the next steering meeting
Next board update in the autumn with the price approach and LIMS plan
Tarnovell Bioscience Group | Confidential 14